## Gantt Chart
WBS ID | Task Name | Start Date | End Date | Duration (Weeks) | Phase | Phase Color
1 | Planning Phase | 2026-04-01 | 2026-04-30 | 4 | Planning | 4472C4
1.1 | Project Initiation and Requirements Scoping | 2026-04-01 | 2026-04-15 | 2 | Planning | 4472C4
1.2 | Technology Selection and 3D Asset Planning | 2026-04-16 | 2026-04-30 | 2 | Planning | 4472C4
2 | Analysis and Design Phase | 2026-05-01 | 2026-06-30 | 8 | Analysis and Design | 70AD47
2.1 | Literature Review and Navigation Training Standards | 2026-05-01 | 2026-05-31 | 4 | Analysis and Design | 70AD47
2.2 | System Architecture, ERD, JSON Schema and UI Wireframes | 2026-06-01 | 2026-06-30 | 4 | Analysis and Design | 70AD47
3 | Implementation Phase (Agile Sprints) | 2026-07-01 | 2026-11-30 | 18 | Implementation | ED7D31
3.1 | 3D Environment and Vessel Assets | 2026-07-01 | 2026-08-15 | 6 | Implementation | ED7D31
3.2 | Simulation Engine and Training Modules | 2026-08-01 | 2026-10-31 | 13 | Implementation | ED7D31
3.3 | Student/Instructor Dashboards and Progress Persistence | 2026-10-15 | 2026-11-30 | 6 | Implementation | ED7D31
3.4 | Helm Bridge, Cameras and Navigation HUD | 2026-09-01 | 2026-10-31 | 8 | Implementation | ED7D31
4 | Testing and Evaluation Phase | 2026-12-01 | 2027-01-31 | 7 | Testing | 7030A0
4.1 | Unit and Integration Testing | 2026-12-01 | 2026-12-24 | 3 | Testing | 7030A0
4.2 | User Acceptance Testing | 2027-01-01 | 2027-01-31 | 4 | Testing | 7030A0
5 | Documentation and Project Closure | 2027-02-01 | 2027-03-31 | 8 | Documentation | A5A5A5
5.1 | Bug Fixing, Performance Tuning and Polish | 2027-02-01 | 2027-02-28 | 4 | Documentation | A5A5A5
5.2 | Final Report, ERD, JSON Schema and Submission | 2027-03-01 | 2027-03-31 | 4 | Documentation | A5A5A5